## Sheet1
S.No | Issue | Type | Environment | Page | Component | Creation Date | Priority | Severity | Raised By | Assigned To | Expected date of completion | Status | Comments
1 | In Platform Enablement page, the component title under Service offerings section is not displaying properly and the text is getting cropped | Defect | Dev | PE | Mosaic | 2018-09-24 | High | Medium | Srivishwapriya Balaji | Tanvi and Team | 2018-10-04 | Open
2 | In Platform Enablement page, configured bannner image URL is not displaying in the image picker text box in edit mode | Observation | Dev | PE | Banner | 2018-09-24 | Medium | Medium | Srivishwapriya Balaji | Tanvi and Team | 2018-10-04 | Open
3 | Something Went wrong message is dsiplaying in Cloud Environment Project Dashboard and CMDB section in CEESO page in IE11 | Defect | Dev | CEESO | Rich Content | 2018-09-26 | High | High | Srivishwapriya Balaji | Tanvi and Team | 2018-10-04 | Open
4 | Something Went wrong message is dsiplaying in Who we are section in OPEE page in IE11 | Defect | Dev | OPEE | Rich Content | 2018-09-26 | High | High | Srivishwapriya Balaji | Tanvi and Team | 2018-10-04 | Open
5 | Banner image section is not aligned properly in CSM page | Defect | Dev | CSM | Banner | 2018-09-26 | High | High | Srivishwapriya Balaji | Tanvi and Team | 2018-10-04 | Open
6 | Roles and Resposibilities title is not displaying in CSM page in IE11 and it is displaying Something went wrong error message | Defect | Dev | CSM | Rich Content | 2018-09-26 | High | High | Srivishwapriya Balaji | Tanvi and Team | 2018-10-04 | Open
7 | Useful links is overlapped with Video in Home Banner component. Please refer the attached screenshot | Defect | Dev | Home | Home Banner | 2018-09-26 | High | High | Srivishwapriya Balaji | Tanvi and Team | 2018-10-04 | Open
8 | Title in Useful links component is not displaying in Bold as given in wireframe and font color of links is displaying in different color and not as per wireframe in Home page | Defect | Dev | Home | Home Banner | 2018-09-28 | Medium | Medium | Srivishwapriya Balaji | Tanvi and Team | 2018-10-04 | Open
9 | Team section is not aligned properly in Home page. Please refer the attached screenshot | Defect | Dev | Home | Links | 2018-09-28 | High | High | Srivishwapriya Balaji | Chandrakant | 2018-10-04 | Open
10 | Arrows in Teams section is not displaying in the same format as shown in wireframe in Home page. Please refer the attached screenshot | Defect | Dev | Home | Links | 2018-09-28 | Medium | Medium | Srivishwapriya Balaji | Chandrakant | 2018-10-04 | Open
11 | Arrow is not displaying for Access page in Modes of Operation section in Home page | Defect | Dev | Home | Rich Tile | 2018-09-28 | Medium | Medium | Srivishwapriya Balaji | Tanvi and Team | 2018-10-04 | Open
12 | Arrow is not displaying for Feedback and Voice of Customer section as given in wireframe in Home Page | Defect | Dev | Home | Rich Tile | 2018-09-28 | Medium | Medium | Srivishwapriya Balaji | Tanvi and Team | 2018-10-04 | Open
13 | Carousel section is not aligned properly in Home page. Article Title is not displaying in Bold, Read More is not dispaying at the bottom right of the section and there is no space between dots at the bottom as per wireframe | Defect | Dev | Home | Carousel | 2018-09-28 | High | High | Srivishwapriya Balaji | Chandrakant | 2018-10-04 | Open
14 | When user clicks on search box without any text, it is redirecting to page not found error page. Entered text in search box is not seen properly in Home Banner component. There is no Go button or search icon to search after entering the text. | Defect | Dev | Home | Home Banner | 2018-09-28 | High | High | Srivishwapriya Balaji | Tanvi and Team | 2018-10-04 | Open
15 | Video in Home Banner component is not playing and getting error. Not displaying in full screen. | Defect | Dev | Home | Home Banner | 2018-09-28 | High | High | Srivishwapriya Balaji | Tanvi and Team | 2018-10-04 | Open
16 | In Carousel component, only 3 items are added, but is displaying fourth and fifth dots. When user clicks on 4th and 5th dots, it is not responding | Defect | Dev | Home | Carousel | 2018-09-28 | High | High | Srivishwapriya Balaji | Chandrakant | 2018-10-04 | Open
17 | When user click on feedback tile in Home page, it is opening in same tab instead of new tab | Defect | Dev | Home | Rich Tile | 2018-09-28 | Medium | Medium | Srivishwapriya Balaji | Tanvi and Team | 2018-10-04 | Open
18 | When user click on Voice of Customer tile in Home page, it is opening in same tab instead of new tab | Defect | Dev | Home | Rich Tile | 2018-09-28 | Medium | Medium | Srivishwapriya Balaji | Tanvi and Team | 2018-10-04 | Open
19 | When user click on Access page in Mode of Operation section in Home page, it is opening in same tab instead of new tab | Defect | Dev | Home | Rich Tile | 2018-09-28 | Medium | Medium | Srivishwapriya Balaji | Tanvi and Team | 2018-10-04 | Open
20 | Links in Team section is not ordered as per the configured order number in Home page | Defect | Dev | Home | Links | 2018-09-28 | High | High | Srivishwapriya Balaji | Chandrakant | 2018-10-04 | Open
21 | Editing doesn't show current data | Defect | QA | All relevant pages | Rich Content | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
22 | EC Font family not available in drop down | Defect | QA | All relevant pages | Rich Content | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
23 | Text resizing is not working | Defect | QA | All relevant pages | Rich Content | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
24 | Fore color is changing the Title color also | Defect | QA | All relevant pages | Rich Content | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
25 | Image not aligned with text when added | Defect | QA | All relevant pages | Rich Content | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
26 | Not able to add any text after the image as image doesn't show up in the Rich Text field | Defect | QA | All relevant pages | Rich Content | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
27 | Image to be center aligned | Defect | QA | All relevant pages | Image Renderer | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
28 | Background image is not rendering | Defect | QA | All relevant pages | Large Tiles | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
29 | last row tiles are going out of the boundry | Defect | QA | All relevant pages | Large Tiles | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
30 | Tile size is too big | Defect | QA | All relevant pages | Large Tiles | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
31 | Tiles should rendered at center of the components | Defect | QA | All relevant pages | Large Tiles | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
32 | current background and fore color of tile not retained while editing | Defect | QA | All relevant pages | Large Tiles | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
33 | Multiple items cannot be selected in manage data form | Defect | QA | All relevant pages | Large Tiles | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
34 | Width is getting strinked once added this webpart to the page only in QA | Defect | QA | Home | Home Banner | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
35 | Search results page url is prepopulated with Dev site URL | Defect | QA | Home | Home Banner | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
36 | Formation of URL to search results page is wrong and link is broken | Defect | QA | Home | Home Banner | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
37 | Link component disable link option is by default set to off, but label is showing it's On | Defect | QA | Home | Home Banner | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
38 | Links component in home banner is not aligned properly | Defect | QA | Home | Home Banner | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
39 | Columns in links component data management form is wrong | Defect | QA | Home | Home Banner | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
40 | Video thumbnail image height should be reduced | Defect | QA | Modes of Operation | Rich Video | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
41 | Position of logo image should be adjusted according to UI | Defect | QA | Home | Tools | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
42 | Each item label should be aligned according to UI | Defect | QA | Home | Tools | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
43 | Space should be given between link text and tile bottom | Defect | QA | Home | Rich Tile | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
44 | Space between arrow image and link text should be reduced | Defect | QA | Home | Rich Tile | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
45 | Rich tile link should be opening in new tab | Defect | QA | Home | Rich Tile | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
46 | Arrow image size should be adjusted according to UI | Defect | QA | Home | Rich Tile | 2018-09-28 | High | High | Arvindhan | Tanvi and Team | 2018-10-04 | Open
47 | Component title font family is wrong | Defect | QA | All relevant pages | Links | 2018-09-28 | High | High | Arvindhan | Chandrakant | 2018-10-04 | Open
48 | Position of logo image should be adjusted according to UI | Defect | QA | All relevant pages | Links | 2018-09-28 | High | High | Arvindhan | Chandrakant | 2018-10-04 | Open
49 | Top, left and Right padding should be adjusted according to UI | Defect | QA | All relevant pages | Links | 2018-09-28 | High | High | Arvindhan | Chandrakant | 2018-10-04 | Open
50 | Only four items are added for carousel, but 5 circles are appearing in the carousel | Defect | QA | All relevant pages | Carousel | 2018-09-28 | High | High | Arvindhan | Chandrakant | 2018-10-04 | Open
51 | Alignment of each team treeview should be fixed according to UI | Defect | QA | All relevant pages | Team Stucture | 2018-09-28 | High | High | Arvindhan | Shilpa | 2018-10-04 | Open
52 | Component title not changed when editing the text in component title property | Defect | QA | All relevant pages | Team Stucture | 2018-09-28 | High | High | Arvindhan | Shilpa | 2018-10-04 | Open
53 | horizantal scroll bar should appear only when content of the component is going out of the boundry | Defect | QA | All relevant pages | Team Stucture | 2018-09-28 | High | High | Arvindhan | Shilpa | 2018-10-04 | Open
54 | Component width is going beyond the webpart zone | Defect | QA | All relevant pages | Team Stucture | 2018-09-28 | High | High | Arvindhan | Shilpa | 2018-10-04 | Open
55 | toggle option for logo image is missing | Defect | QA | All relevant pages | Team Stucture | 2018-09-28 | High | High | Arvindhan | Shilpa | 2018-10-04 | Open
56 | Logo and alignment issues | Defect | QA | All relevant pages | Modes of Operation | 2018-09-28 | High | High | Arvindhan | Arvindhan | 2018-10-04 | Open
57 | Search is not working when enter the text in Search box and click on search icon | Defect | QA | All relevant pages | Search | 2018-09-28 | High | High | Arvindhan | Arvindhan | 2018-10-04 | Open
58 | Search results web part of files is not hidden once the page is loaded | Defect | QA | All relevant pages | Search | 2018-09-28 | High | High | Arvindhan | Arvindhan | 2018-10-04 | Open
59 | Alignment issues with search results item label and icon | Defect | QA | All relevant pages | Search | 2018-09-28 | High | High | Arvindhan | Arvindhan | 2018-10-04 | Open
60 | remove the about # of results | Defect | QA | All relevant pages | Search | 2018-09-28 | High | High | Arvindhan | Arvindhan | 2018-10-04 | Open